## Gap Analysis Summary
MedSecure Cloud Platform (MSCP) — Gap Analysis Summary
NIST SP 800-53 Rev 5 · HIPAA / HITECH · Partially Effective Controls
Control ID | Control Name | Security Topic | Identified Gap | Risk if Unaddressed | Recommendation | Priority
AC-6 | Least Privilege | Identity & Access Management | RBAC applied but vendor access reviews are not consistently documented. No formal periodic role re-certification process is in place for all roles. | Excessive vendor or user privileges could lead to unauthorized access to ePHI, violating HIPAA §164.312(a)(1) and increasing insider threat risk. | Implement quarterly automated access reviews using Azure AD Access Reviews. Enforce formal role re-certification workflows triggered by HR and documented in the IAM system. | High
AC-2 | Account Management | Identity & Access Management | Account lifecycle is managed via HR-triggered workflows but lacks full automation coverage. Vendor time-bound accounts are not consistently monitored for expiry. | Orphaned or expired vendor accounts increase the risk of unauthorized access to clinical and billing data, potentially resulting in a HIPAA breach and regulatory penalty. | Automate account deprovisioning using Azure AD Lifecycle Workflows. Configure alerts for accounts approaching expiry and conduct monthly audits of vendor account status. | High
AU-6 | Audit Review & Analysis | Audit & Logging | Automated analytics rules in Microsoft Sentinel are still in development. Manual log review processes create gaps in anomaly detection coverage. | Delayed or missed detection of unauthorized access or data exfiltration events, increasing attacker dwell time and severity of HIPAA breach impact. | Accelerate deployment of Sentinel analytics rules and automated playbooks. Define SLAs for alert triage (Critical: 1 hour, High: 4 hours). Document and test escalation procedures. | High
SI-4 | System Monitoring | System Monitoring | Real-time monitoring is operational but automated playbooks for incident response are still in development. Monitoring coverage gaps exist across some application layers. | Without automated response playbooks, incident containment relies on manual intervention, increasing response time and potential damage from active threats or APT activity. | Complete development and testing of automated Sentinel playbooks for common incident types. Expand monitoring coverage to all application layers. Conduct tabletop exercises quarterly. | High
CM-2 | Baseline Configuration | Configuration Management | Azure Policy enforces some baselines but full automation of configuration compliance is still in progress. Baseline deviation tracking is incomplete for all resource types. | Misconfigured resources may expose vulnerabilities, create compliance drift, and increase the attack surface for exploitation of cloud infrastructure. | Complete Azure Policy automation for all resource types. Integrate Defender for Cloud secure score into weekly reporting. Define remediation SLAs for policy violations. | Medium
RA-5 | Vulnerability Scanning | Configuration Management | Vulnerability scans are conducted regularly but remediation backlog management lacks formal tracking and accountability. SLA compliance for Critical and High findings is not consistently measured. | Unpatched critical vulnerabilities could be exploited by threat actors, resulting in unauthorized access to ePHI and potential HIPAA breach notification requirements. | Implement a formal vulnerability remediation tracking process with assigned owners. Automate SLA compliance reporting in Defender for Cloud. Escalate overdue Critical findings to CISO. | High
CA-7 | Continuous Monitoring | Configuration Management | Monitoring strategy and cadence documentation is in progress but not yet finalized. Risk dashboard exists but lacks standardized metrics and reporting frequency. | Without a formalized monitoring strategy, coverage gaps may go undetected and compliance posture cannot be reliably demonstrated to auditors or regulators. | Finalize and publish the continuous monitoring strategy document. Define standardized metrics, reporting cadence, and responsible owners. Schedule quarterly strategy reviews. | Medium

## Risk Register
MedSecure Cloud Platform (MSCP) — Risk Register
NIST SP 800-53 Rev 5 · HIPAA / HITECH · Identified from Gap Analysis
Risk ID | Description | Likelihood | Impact | Risk Level | Recommendation | Related Control
RR-001 | Insufficient vendor access reviews may allow excessive privileges to persist, enabling unauthorized access to ePHI systems. | Medium | High | High | Implement quarterly Azure AD Access Reviews with formal role re-certification and documented approval workflows. | AC-6
RR-002 | Orphaned or expired vendor accounts not deprovisioned in a timely manner create unauthorized access pathways to clinical data. | Medium | High | High | Automate account deprovisioning via Azure AD Lifecycle Workflows and conduct monthly audits of vendor account expiry status. | AC-2
RR-003 | Incomplete Sentinel analytics rules create gaps in anomaly detection, increasing attacker dwell time before detection. | High | High | High | Accelerate Sentinel rule deployment. Define and enforce alert triage SLAs. Test and document escalation procedures. | AU-6
RR-004 | Absence of automated incident response playbooks results in slow manual containment during active security incidents. | Medium | High | High | Complete and test automated Sentinel playbooks for common incident types. Conduct quarterly tabletop exercises. | SI-4
RR-005 | Incomplete baseline configuration automation allows configuration drift, expanding the attack surface across Azure resources. | Medium | Medium | Medium | Complete Azure Policy automation. Integrate secure score reporting. Define and enforce remediation SLAs for policy violations. | CM-2
RR-006 | Vulnerability remediation backlog lacks formal tracking and SLA accountability, leaving critical findings unpatched. | High | High | High | Assign remediation owners. Automate SLA compliance tracking in Defender for Cloud. Escalate overdue Critical findings to CISO. | RA-5
RR-007 | Undocumented continuous monitoring strategy prevents consistent compliance demonstration and may mask coverage gaps. | Low | Medium | Medium | Finalize monitoring strategy document. Define metrics, reporting cadence, and owners. Schedule quarterly strategy reviews. | CA-7
RISK LEVEL LEGEND
High — Immediate action required
Medium — Action required within 30 days
Low — Monitor and review quarterly