## Cover
MedSecure Cloud Platform (MSCP)
Plan of Action and Milestones (POA&M)
NIST SP 800-53 Rev 5 · HIPAA / HITECH · Azure Healthcare Platform
System Name | MedSecure Cloud Platform (MSCP)
System Description | Azure-hosted healthcare platform for secure storage, processing, and transmission of ePHI
System Owner | Ashley Miller, GRC Analyst
POA&M Preparer | Ashley Miller
Applicable Frameworks | NIST SP 800-53 Rev 5 ¦ HIPAA/HITECH ¦ NIST RMF
Date Prepared | June 2026
Total Findings | 10
Critical Findings | 1
High Findings | 5
Moderate Findings | 4
POA&M Status | Active — Remediation In Progress

## POA&M Tracker
MedSecure Cloud Platform — Plan of Action and Milestones (POA&M) Tracker
NIST RMF Step 5 · Authorization Support · June 2026
POA&M ID | Weakness Description | NIST SP 800-53 Control ID | HIPAA Citation | Risk Rating | Scheduled Completion Date | Milestones | Responsible POC | Resources Required | Status | Progress Notes | Date Closed
MSCP-001 | MFA not enforced for all privileged and remote access accounts. Users can authenticate with single-factor credentials, increasing risk of unauthorized access to ePHI. | IA-2, AC-17 | HIPAA §164.312(d) — Person Authentication | HIGH | Aug 2026 | 1. Audit all privileged accounts for MFA enrollment 2. Enable Entra ID Conditional Access MFA policies 3. Enforce MFA for all remote access sessions 4. Validate and document compliance | Ashley Miller | Microsoft Entra ID P2 License, Azure Conditional Access | Open | MFA policies drafted. Awaiting Conditional Access rule deployment and testing.
MSCP-002 | Privileged account access reviews are ad hoc with no documented quarterly review schedule or formal re-certification process for all user roles. | AC-2, AC-6 | HIPAA §164.308(a)(3) — Workforce Access Management | MODERATE | Sep 2026 | 1. Define quarterly access review schedule 2. Configure Azure AD Access Reviews 3. Document re-certification workflow and approvers 4. Complete first formal review cycle | Ashley Miller | Azure AD Access Reviews (Entra ID P2) | Open | Review schedule drafted. Azure AD Access Review configuration pending.
MSCP-003 | Azure Key Vault key rotation is not automated. Manual rotation processes introduce risk of expired or compromised cryptographic keys remaining in use. | SC-12, SC-13 | HIPAA §164.312(a)(2)(iv) — Encryption and Decryption | HIGH | Jul 2026 | 1. Enable automated key rotation in Azure Key Vault 2. Set rotation policy for all encryption keys 3. Configure expiration alerts 4. Document key lifecycle procedures | Ashley Miller | Azure Key Vault (standard tier) | In Progress | Key Vault rotation policies under configuration. Alert thresholds being tested.
MSCP-004 | Vulnerability scanning cadence is undefined. No formal schedule, report archiving process, or SLA for Critical/High finding remediation is documented. | RA-5, CA-7 | HIPAA §164.308(a)(8) — Evaluation | HIGH | Aug 2026 | 1. Define vulnerability scanning schedule (weekly automated) 2. Configure Defender for Cloud scan reporting 3. Establish remediation SLAs (Critical: 15 days, High: 30 days) 4. Implement scan report archiving | Ashley Miller | Microsoft Defender for Cloud, Tenable (if applicable) | Open | Scanning cadence under definition. Defender for Cloud partially configured.
MSCP-005 | Audit log integrity and immutability has not been formally validated. No process exists to verify logs have not been tampered with or deleted. | AU-6, AU-12 | HIPAA §164.312(b) — Audit Controls | MODERATE | Sep 2026 | 1. Enable Azure Monitor immutable log storage 2. Configure log integrity alerts in Sentinel 3. Document log validation procedures 4. Test and validate retention settings | Ashley Miller | Azure Monitor, Microsoft Sentinel, Immutable Storage | Open | Log storage configuration in progress. Immutability settings being reviewed.
MSCP-006 | Patch management baseline and remediation SLAs are not formally documented. No tracked process exists for ensuring timely patching of critical vulnerabilities. | CM-2, SI-2 | HIPAA §164.308(a)(5) — Security Awareness and Training | MODERATE | Aug 2026 | 1. Define patch management baseline and SLA matrix 2. Configure Azure Update Manager 3. Establish patching approval workflow 4. Document and test process end-to-end | Ashley Miller | Azure Update Manager, Change Control Board | Open | Patch SLA matrix under development. Azure Update Manager review pending.
MSCP-007 | Continuous monitoring strategy has not been formally documented. Risk dashboard exists but lacks standardized metrics, defined reporting cadence, and ownership. | CA-7 | HIPAA §164.308(a)(8) — Evaluation | MODERATE | Sep 2026 | 1. Draft continuous monitoring strategy document 2. Define standardized metrics and KPIs 3. Establish reporting cadence and owners 4. Publish and schedule quarterly reviews | Ashley Miller | Microsoft Sentinel, Azure Monitor, GRC Documentation Tools | Open | Strategy document outline drafted. Metrics framework in development.
MSCP-008 | Third-party vendor assessments and Business Associate Agreements (BAAs) have not been fully completed and documented for all vendors with ePHI access. | SA-9, AC-20 | HIPAA §164.308(b)(1) — Business Associate Contracts | HIGH | Aug 2026 | 1. Inventory all third-party vendors with ePHI access 2. Verify BAA status for each vendor 3. Conduct risk assessment for unvetted vendors 4. Document assessment results and BAA registry | Ashley Miller | Vendor Management Platform, Legal/Compliance Review | Open | Vendor inventory in progress. BAA gap list being compiled.
MSCP-009 | Just-in-Time (JIT) access is not enabled for administrative accounts. Remote administrative access paths are not fully documented or time-limited. | AC-6, AC-17 | HIPAA §164.312(a)(1) — Access Control | HIGH | Jul 2026 | 1. Enable JIT access in Microsoft Defender for Cloud 2. Document all remote admin access paths 3. Configure time-limited access approvals 4. Validate and test JIT workflow | Ashley Miller | Microsoft Defender for Cloud JIT, Azure RBAC | In Progress | JIT configuration in progress in Defender for Cloud. Access path documentation begun.
MSCP-010 | No formal incident response (IR) plan exists for the MSCP platform. There are no documented procedures for detection, containment, eradication, or post-incident review of security events involving ePHI. | IR-1, IR-4, IR-8 | HIPAA §164.308(a)(6) — Security Incident Procedures | CRITICAL | Jul 2026 | 1. Develop formal IR plan aligned with NIST SP 800-61 2. Define roles, responsibilities, and escalation paths 3. Configure Sentinel automated IR playbooks 4. Conduct tabletop exercise to validate plan | Ashley Miller | Microsoft Sentinel Playbooks, NIST SP 800-61 Reference, Legal/Compliance | Open | CRITICAL — IR plan development is highest priority remediation item. Draft outline in progress.

## Summary Dashboard
MSCP POA&M — Summary Dashboard
As of June 2026 · 10 Total Findings
Risk Level | Finding Count | % of Total
CRITICAL | 1 | 10%
HIGH | 5 | 50%
MODERATE | 4 | 40%
LOW | 0 | 0%
Status | Count
Open | 8
In Progress | 2
Closed | 0
⚠ CRITICAL: MSCP-010 — No incident response plan exists. Highest priority remediation item.
🔴 HIGH: MSCP-001 MFA gaps ¦ MSCP-003 Key rotation ¦ MSCP-004 Vuln scanning ¦ MSCP-008 BAAs ¦ MSCP-009 JIT access